## Project Profile
Query Tracking Sheet Template
PVV/ETR01/TMP
Project Code
Project Name
Prepared/Modified by | Role | Date of Preparation
Reviewed by | Role | Date of Review
Approved by | Role | Date of Approval
Circulation List |  | Version Number of the template: 1.0
Version Number | <version No >

## Readme
Guidelines for usage of the Query Tracking Sheet
1 | Enter all requirements related queries raised throught project duration in this sheet to keep all queries at one place.
2 | Insert queries raised and answered in proposal phase as well into this sheet, when the project begins. This will ensure all replies and assumptions made in proposal phase are knows to the development team.
3 | Projects send/receive updated query tracking sheet to/from Customer /Capgemini. Only the latest version of the sheet should be maintained at designated place (to avoid confusion/rework). The designated locatin should be pointed to by Projects' .
4 | Projects should request Customer /Customer Collaborator(CC) to enter their queries and replies also in this sheet. Even if customer does not enter, Projects should keep this sheet updated for important queries, if queries are received by mails or documents.
5 | The status of all pending queries should be taken in the project meetings and Status Reveiw. PL should escalate to Customer Collaborator/Customer for open queries.

## Query Sheet
<<Type Project Id here and remove the brackets>> |  |  | 100378124
Query Tracking Sheet
Sr # | Type | Module | Query Text | Reply Text | Raised By (Name) | Open (Date) | Reply By (Name) | Closed (Date) | Phase Raised In | Phase Closed in | CR (Y/N) | Status | Query TAT (Turn Around Time) in days
1 | QP | Login | Is there a need to sign up for new customer. |  | Rashmi Wani | 20/10/2018 | Sangeetha | 20/10/2018 | Designing |  | N | Closed | 1
2 | QP | Update | Where to upload the document as asked in case study. |  | Arnav Acharya | 20/10/2018 | Sangeetha | 20/10/2018 | Designing |  | N | Closed | 1
3 | QP | Update | What are the types of endorsements to be done by the customer. |  | Nikhil Rupainwar | 20/10/2018 | Sangeetha | 20/10/2018 | Designing |  | N | Closed | 1
4 | QP | Database | What are audit columns in tables as asked in our Case Study over ePES. |  | Nikhil Rupainwar | 25/10/2018 | Shital |  | Designing |  | N
Note on B4: QC = Q by Client QP = Q by IGate
Note on L4: Has this query resulted in a CR (record shd be present in the CR tracking Sheet)
Note on M4: Open Active Closed On-hold
Note on N4: TAT is the difference in days between the time query is raised to the time query is closed. Average TAT can be included be in the weekly status report to the client

## Revision History
REVISION HISTORY OF WORK PRODUCT (to be maintained by projects)
# | Date | Version # | Section Changed | Details of changes made | Approved By